## Sheet1
Month	Goals
1	- write introduction, background + related work (on DSPLs and context-based adaptation in EPS) chapters
(15.11.-15.12.)	- set up and look into existing AdaptiveCEP code base

2	- design of the CFM: requirement analysis w.r.t. AdaptiveCEP, model design and justification of choices
(16.12.-15.1.)	- design of mechanism transition approach + idea how to implement it
	- basic implementation of the model into AdaptiveCEP, including necessary adaptations of code base

3	- finish implementation of CFM and implement mechanism transition approach
(16.1.-15.2.)	- test implementation, bug fixes etc.
	- formulate simulation/evaluation goals
	- design simulation scenario, basic setup of simulation
	- finalize introduction, background + related work

4	- begin evaluation, adapt implementation (or design) as necessary
(16.2.-15.3.)	- design and setup of more involved simulations
	- finalize design and implementation chapters

5
(16.3.- 1.4.)	- analyze evaluation results in detail
	- extend and finalize evaluation chapter

6	- complete thesis document
(2.4.-30.4.)	- revise thesis document
	- prepare presentation